## EVENTS
Event Planning Template
|  | Date of event: | 2025-05-31 | 2025-05-26 | 2025-05-31
| CODE | TASK | WEEKS OUT | START | END | WHO | NOTES
ü | AD | Establish purpose and goal/define event | 30 | 2024-10-28 | 2024-11-02
ü | FR | Research/approach event chair(s) | 30 | 2024-10-28 | 2024-11-02
ü | AD | Research/appoint Event Manager | 30 | 2024-10-28 | 2024-11-02
ü | L | Visit possible sites | 29 | 2024-11-04 | 2024-11-09
| FR | Compile mailing lists, gather prospect lists from co-hosts, friends | 29 | 2024-11-04 | 2024-11-09
ü | FR | Form committee(s) if necessary | 28 | 2024-11-11 | 2024-11-16
| AD | Decide ticket prices | 27 | 2024-11-18 | 2024-11-23
ü | VC | Recruit VIP/Celebrities lead | 27 | 2024-11-18 | 2024-11-23
| AD | Get cost estimates | 26 | 2024-11-25 | 2024-11-30
| AD | Draft initial budget | 26 | 2024-11-25 | 2024-11-30
| FR | Seek underwriting/sponsorship | 26 | 2024-11-25 | 2024-11-30
ü | L | Pick a date, check for conflicts | 26 | 2024-11-25 | 2024-11-30
ü | L | Secure venue and get written agreement | 26 | 2024-11-25 | 2024-11-30
ü | AD | Produce timeline | 26 | 2024-11-25 | 2024-11-30
ü | ED | Recruit Event Design lead | 25 | 2024-12-02 | 2024-12-07
| VC | Invite/confirm VIPs and/or entertainment | 25 | 2024-12-02 | 2024-12-07
ü | VD | Recruit Video lead | 25 | 2024-12-02 | 2024-12-07
ü | PM | Pick graphic artist, begin graphic design | 24 | 2024-12-09 | 2024-12-14
| AD | Investigate needs for special permits, insurance, etc. | 24 | 2024-12-09 | 2024-12-14
| FR | Begin solicitation of auction items, food/beverage donations, prizes, etc. | 24 | 2024-12-09 | 2024-12-14
| PM | Research and hire printer | 21 | 2024-12-30 | 2025-01-04
| L | Research and hire award makers | 21 | 2024-12-30 | 2025-01-04
ü | VD | Initial meeting/video ideas | 20 | 2025-01-06 | 2025-01-11
| AD | Contract with all vendors | 20 | 2025-01-06 | 2025-01-11
| VD | Draft creative brief/outline | 18 | 2025-01-20 | 2025-01-25
| C | Determine food and drink needs & determine whether to buy or get in kind | 18 | 2025-01-20 | 2025-01-25
| C | Hire caterer or solicit food and drink | 16 | 2025-02-03 | 2025-02-08
| VD | Compile raw footage, photos, etc. | 15 | 2025-02-10 | 2025-02-15
| C | Get written agreement from caterer or in-kind contributor | 15 | 2025-02-10 | 2025-02-15
| AD | Determine process for RSVP intake & set up system | 15 | 2025-02-10 | 2025-02-15
| ED | Event Design rough ideas | 15 | 2025-02-10 | 2025-02-15
| PM | Draft and approve invitation and RSVP copy | 14 | 2025-02-17 | 2025-02-22
| PM | Pick designer for journal | 14 | 2025-02-17 | 2025-02-22
| FR | Finalize all sponsorship agreements (including media) | 13 | 2025-02-24 | 2025-03-01
| FR | Complete compilation of mailing list and quality control | 13 | 2025-02-24 | 2025-03-01
| VC | Written confirmation of celebrity/entertainment | 13 | 2025-02-24 | 2025-03-01
| AD | Apply for permits, license, insurance riders, etc. | 13 | 2025-02-24 | 2025-03-01
| C | Set menu | 12 | 2025-03-03 | 2025-03-08
| FR | Send a Save the Date card/email | 12 | 2025-03-03 | 2025-03-08
| ED | Finalize Event Design | 12 | 2025-03-03 | 2025-03-08
| ED | Rough out floor plan | 12 | 2025-03-03 | 2025-03-08
| PR | First press release and calendar listings sent | 12 | 2025-03-03 | 2025-03-08
| PM | Design and approve design for invitation and RSVP | 12 | 2025-03-03 | 2025-03-08
| AD | Update timeline & budget | 12 | 2025-03-03 | 2025-03-08
| FR | Personalized solicitation letters to key prospects before invitation mailing | 11 | 2025-03-10 | 2025-03-15
| PM | Print invitation and RSVP cards | 10 | 2025-03-17 | 2025-03-22
| PM | Begin copywriting and design of journal | 10 | 2025-03-17 | 2025-03-22
| FR | Prepare invitation list from database and co-hosts, including email addresses | 10 | 2025-03-17 | 2025-03-22
| VD | First draft | 9 | 2025-03-24 | 2025-03-29
| PM | Distribute posters (if any) | 9 | 2025-03-24 | 2025-03-29
| L | Plan/finalize transportation/accommodations for VIPs | 9 | 2025-03-24 | 2025-03-29
| ED | Obtain contracts for rentals | 9 | 2025-03-24 | 2025-03-29
| PR | Press releases about VIPs/celebs/honorees | 9 | 2025-03-24 | 2025-03-29
| FR | Follow-up solicitation of key prospects by all committee members | 9 | 2025-03-24 | 2025-03-29
| FR | Arrange for co-hosts to personalize their invitations | 9 | 2025-03-24 | 2025-03-29
| PM | Receive invitations from printer | 9 | 2025-03-24 | 2025-03-29
| L | Review needs for the day of event | 8 | 2025-03-31 | 2025-04-05
| L | Walk through at site with all key vendors and parties | 8 | 2025-03-31 | 2025-04-05
| L | Produce volunteer plan | 8 | 2025-03-31 | 2025-04-05
| FR | Personalize and mail invitations | 8 | 2025-03-31 | 2025-04-05
| AD | Update timeline & budget | 8 | 2025-03-31 | 2025-04-05
| AD | Process RSVPs (daily) | 7 | 2025-04-07 | 2025-04-12
| AD | Create interim financial reports (weekly) | 7 | 2025-04-07 | 2025-04-12
| L | Solicit volunteers | 7 | 2025-04-07 | 2025-04-12
| L | Solicit photographer/videographer | 7 | 2025-04-07 | 2025-04-12
| VD | Second draft | 6 | 2025-04-14 | 2025-04-19
| PR | Follow-up with news media | 6 | 2025-04-14 | 2025-04-19
| FR | Follow up on invitations | 6 | 2025-04-14 | 2025-04-19
| FR | Support co-hosts in their follow-up | 6 | 2025-04-14 | 2025-04-19
| VC | Confirm participation with details for VIPs celebrities | 5 | 2025-04-21 | 2025-04-26
| ED | Get final site plan | 5 | 2025-04-21 | 2025-04-26
| L | Write day of event plan of operation (security, logistics, etc.) | 5 | 2025-04-21 | 2025-04-26
| L | Send copy to awards vendor | 5 | 2025-04-21 | 2025-04-26
| L | Order special Day of Event Supplies (radios, etc.) | 4 | 2025-04-28 | 2025-05-03
| L | Draft program order | 4 | 2025-04-28 | 2025-05-03
| L | Draft script | 4 | 2025-04-28 | 2025-05-03
| AD | Update timeline & budget | 4 | 2025-04-28 | 2025-05-03
| VD | Final video | 3 | 2025-05-05 | 2025-05-10
| PM | Deadline for journal copy | 3 | 2025-05-05 | 2025-05-10
| PM | Journal to printer | 3 | 2025-05-05 | 2025-05-10
| L | Deadline for gift bag contents, assemble | 2 | 2025-05-12 | 2025-05-17
| EV | Set debriefing date | 2 | 2025-05-12 | 2025-05-17
| C | Give caterer final numbers | 2 | 2025-05-12 | 2025-05-17
| L | Plan all ground transportation needs | 2 | 2025-05-12 | 2025-05-17
| L | Confirm all deliveries | 2 | 2025-05-12 | 2025-05-17
| L | Compile packing list | 2 | 2025-05-12 | 2025-05-17
| L | Go on a walkthrough of the venue | 2 | 2025-05-12 | 2025-05-17
| L | Enlist, assign, train on-site event personnel | 2 | 2025-05-12 | 2025-05-17
| L | Draft check-in procedures | 2 | 2025-05-12 | 2025-05-17
| L | Prepare on-site personnel/production schedule | 2 | 2025-05-12 | 2025-05-17
| L | Delivery of awards | 2 | 2025-05-12 | 2025-05-17
| AD | Update timeline & budget | 1 | 2025-05-19 | 2025-05-24
| L | Finalize registration/check-in system | 1 | 2025-05-19 | 2025-05-24
| L | Orient volunteers | 1 | 2025-05-19 | 2025-05-24
| L | Distribute final scripts/programs to all VIPs and key people | 1 | 2025-05-19 | 2025-05-24
| L | Reconfirm all logistics | 1 | 2025-05-19 | 2025-05-24
| L | Maintain updated itinerary | 1 | 2025-05-19 | 2025-05-24
| PR | Send press advisories | 1 | 2025-05-19 | 2025-05-24
| L | Secure petty cash and needed checks | 1 | 2025-05-19 | 2025-05-24
| L | Pack | 1 | 2025-05-19 | 2025-05-24
| C | Confirm caterer | 1 | 2025-05-19 | 2025-05-24
| PM | Journal delivery | 0 | 2025-05-26 | 2025-05-31
| AD | Prepare guest list | 0 | 2025-05-26 | 2025-05-31
| L | Arrive early with clothes, petty cash and checks | 0 | 2025-05-26 | 2025-05-31
| L | Establish production area onsite | 0 | 2025-05-26 | 2025-05-31
| ED | Oversee final set-up | 0 | 2025-05-26 | 2025-05-31
| L | Final tech rehearsal (sound, light, video) | 0 | 2025-05-26 | 2025-05-31
| C | Go over details with caterer | 0 | 2025-05-26 | 2025-05-31
| L | Be sure all key VIPs/volunteers have their key documents | 0 | 2025-05-26 | 2025-05-31
| PR | Final calls/faxes/emails to the media | 0 | 2025-05-26 | 2025-05-31
| L | Set up and hold event | 0 | 2025-05-26 | 2025-05-31
| ED | Return rentals | 0 | 2025-05-26 | 2025-05-31
| FR | Call key people and thank them | -1 | 2025-06-02 | 2025-06-07
| VC | Send VIPs/celebs thank yous | -1 | 2025-06-02 | 2025-06-07
| FR | Make list of thank yous | -1 | 2025-06-02 | 2025-06-07
| FR | Draft thank you letter to all attendees | -1 | 2025-06-02 | 2025-06-07
| FR | Add names and information to database | -1 | 2025-06-02 | 2025-06-07
| FR | Invoice uncollected monies (if any) | -1 | 2025-06-02 | 2025-06-07
| EV | Evaluate event/have debriefing meeting | -2 | 2025-06-09 | 2025-06-14
| FR | Prepare and send thank-you letters | -2 | 2025-06-09 | 2025-06-14
| FR | Identify and follow up on any opportunities created | -2 | 2025-06-09 | 2025-06-14
| AD | Create final financial report | -3 | 2025-06-16 | 2025-06-21
| EV | Write up and file final recommendations | -3 | 2025-06-16 | 2025-06-21
Key:
| AD | Administrative
| C | Catering
| ED | Event design
| EV | Evaluation
| FR | Fundraising
| L | Logistics
| PM | Printed materials
| PR | Public relations, media
| VC | VIPs and celebrities
| VD | Video
Formulas:
START = E2-([WEEKS OUT]*7)
END = [START]+5